## Slide 1
South Africa
market story
review
Agreed scope and work programme
Durban and the Lesedi catchment
7 October 2026
Scope signed off | Analysis pending
Photo source: Royal Vopak | Terminal Durban | vopak.com
Strictly Confidential
Notes: Speaker note: Walk through four sections: the project question, the analytical
requirements, the model-build problem and the delivery approach. The purpose is to
connect the analyst's tasks to the decisions the engagement needs to support.
Week 1 analytical pack, 6 October 2026. Existing kickoff cover/closing reused at user request.
SCR delivery order: page 1 of 16. Gap IDs and original evidence references retained in notes.
SCR delivery order: page 1 of 16. Gap IDs and original evidence references retained in notes.
SCR delivery order: page 1 of 16. Gap IDs and original evidence references retained in notes.
SCR delivery order: page 1 of 16. Gap IDs and original evidence references retained in notes.
SCR delivery order: page 1 of 16. Gap IDs and original evidence references retained in notes.
SCR delivery order: page 1 of 16. Gap IDs and original evidence references retained in notes.
SCR delivery order: page 1 of 16. Gap IDs and original evidence references retained in notes.
SCR delivery order: page 1 of 16. Gap IDs and original evidence references retained in notes.
SCR delivery order: page 1 of 16. Gap IDs and original evidence references retained in notes.
SCR delivery order: page 1 of 16. Gap IDs and original evidence references retained in notes.
SCR delivery order: page 1 of 16. Gap IDs and original evidence references retained in notes.
SCR delivery order: page 1 of 16. Gap IDs and original evidence references retained in notes.
6 October SCR editorial pass: presentation copy and map hierarchy only. Source observations, example volumes and model inputs unchanged.
SCR delivery order: page 1 of 16. Gap IDs and original evidence references retained in notes.
6 October SCR editorial pass: presentation copy and map hierarchy only. Source observations, example volumes and model inputs unchanged.
SCR delivery order: page 1 of 16. Gap IDs and original evidence references retained in notes.
6 October SCR editorial pass: presentation copy and map hierarchy only. Source observations, example volumes and model inputs unchanged.
SCR delivery order: page 1 of 16. Gap IDs and original evidence references retained in notes.
6 October SCR editorial pass: presentation copy and map hierarchy only. Source observations, example volumes and model inputs unchanged.
SCR delivery order: page 1 of 16. Gap IDs and original evidence references retained in notes.
6 October SCR editorial pass: presentation copy and map hierarchy only. Source observations, example volumes and model inputs unchanged.
SCR delivery order: page 1 of 16. Gap IDs and original evidence references retained in notes.
6 October SCR editorial pass: presentation copy and map hierarchy only. Source observations, example volumes and model inputs unchanged.
SCR delivery order: page 1 of 16. Gap IDs and original evidence references retained in notes.
6 October SCR editorial pass: presentation copy and map hierarchy only. Source observations, example volumes and model inputs unchanged.
Convergence order: national accounting p3; provincial map p4; history/estimates p5. Current page 1.
SCR delivery order: page 1 of 16. Gap IDs and original evidence references retained in notes.
6 October SCR editorial pass: presentation copy and map hierarchy only. Source observations, example volumes and model inputs unchanged.
Convergence order: national accounting p3; provincial map p4; history/estimates p5. Current page 1.
SCR delivery order: page 1 of 16. Gap IDs and original evidence references retained in notes.
6 October SCR editorial pass: presentation copy and map hierarchy only. Source observations, example volumes and model inputs unchanged.
Convergence order: national accounting p3; provincial map p4; history/estimates p5. Current page 1.
Final structure: baseline pp3–6; changes pp7–11 (forecast framework p9); outlook pp12–17 (market choices p16, inventory p17). Current page 1.
SCR delivery order: page 1 of 16. Gap IDs and original evidence references retained in notes.
6 October SCR editorial pass: presentation copy and map hierarchy only. Source observations, example volumes and model inputs unchanged.
Convergence order: national accounting p3; provincial map p4; history/estimates p5. Current page 1.
Final structure: baseline pp3–6; changes pp7–11 (forecast framework p9); outlook pp12–17 (market choices p16, inventory p17). Current page 1.

## Slide 2: The agreed review connects market evidence to Vopak's investment opportunity
1 Overview
2 Market baseline
3 Market changes
4 Vopak outlook
Approval covers this review scope and work programme. It does not verify data or approve model results.
Scope signed off on 7 October 2026 | Analysis and investment conclusions remain to be completed
Story stage | Question to answer | Required output
Situation | How have South African fuel demand and domestic supply developed? | Historical exhibits and an evidence audit covering six themes.
Complication | Which trends could persist or reverse, and where do constraints arise? | Four explicit complications, supported by scenario levers.
Resolution | What is Vopak's share in Durban and the Lesedi catchment? Is further investment justified? | Current and scenario shares, capacity headroom and conditional investment conclusions.
Strictly Confidential
Notes: Source: user feedback and explicit scope sign-off in this conversation, 7 October 2026. Style and existing coverage references: Vopak_Convergence_current.pptx, inspected 7 October 2026. Repository boundaries: CLAUDE.md; GATE_CHECKLIST.md; workstreams/README.md. No new market research or quantitative findings are asserted. Approval covers this review scope and work programme. It does not verify data or approve model results.

## Slide 3: Demand history needs a stronger economic and vehicle-use explanation
1 Overview
2 Market baseline
3 Market changes
4 Vopak outlook
Existing pack starting points: slides 16-17, 19 and 21. Coverage references are not source validation.
Situation | Working hypotheses to verify; existing coverage to audit
Theme | Evidence and exhibit | Work required
Growth and investment | Petrol/diesel volumes alongside real GDP, fixed investment, FDI and confidence. | Test the view that volumes were broadly flat over the past decade; explain COVID and recovery. Separate economic weakness from structural change.
Fuel prices and EVs | Fuel-price history and paths linked to EV purchase prices and fuel/electricity running costs. | Existing price assumptions need an ownership-cost exhibit. Distinguish geopolitical shocks from sustained changes; calibrate adoption response.
Vehicle efficiency | OEM historical and expected consumption rates by segment; fleet growth and replacement. | Translate new-vehicle gains through fleet turnover and real-world use. Show the net fuel effect of fleet size, mileage and efficiency; separate EV switching.
Strictly Confidential
Notes: Source: user feedback and explicit scope sign-off in this conversation, 7 October 2026. Style and existing coverage references: Vopak_Convergence_current.pptx, inspected 7 October 2026. Repository boundaries: CLAUDE.md; GATE_CHECKLIST.md; workstreams/README.md. No new market research or quantitative findings are asserted. Existing pack starting points: slides 16-17, 19 and 21. Coverage references are not source validation.

## Slide 4: Power and freight need evidence that translates activity into diesel volumes
1 Overview
2 Market baseline
3 Market changes
4 Vopak outlook
Existing pack starting points: slides 16-17 and 19. Transnet's cited target remains unverified in this review.
Situation | Establish separate baselines before introducing scenario levers
Theme | Evidence and exhibit | Work required
Eskom diesel | Annual diesel volumes and expenditure alongside EAF and diesel generation. | Align periods and plant coverage. Verify the proposed relationship between improved EAF and lower diesel use; obtain consumption rates.
Power-system plans | Fleet retirement/decommissioning and replacement wind, solar and gas commissioning plans. | Record timing, capacity and delivery uncertainty. Keep Eskom and non-Eskom diesel demand separate.
Road and rail freight | Historical payloads by corridor and commodity; road/rail network overlay and planned rail capacity. | Verify the cited Transnet ambition of 250 Mt by 2030. Confirm the roughly four national road corridors; identify transferable freight, haul distances and net diesel effects.
Strictly Confidential
Notes: Source: user feedback and explicit scope sign-off in this conversation, 7 October 2026. Style and existing coverage references: Vopak_Convergence_current.pptx, inspected 7 October 2026. Repository boundaries: CLAUDE.md; GATE_CHECKLIST.md; workstreams/README.md. No new market research or quantitative findings are asserted. Existing pack starting points: slides 16-17 and 19. Transnet's cited target remains unverified in this review.

## Slide 5: The domestic supply timeline must include Secunda and Mossgas
1 Overview
2 Market baseline
3 Market changes
4 Vopak outlook
Existing pack starting points: slides 4, 6 and 26. Proposed integrated exhibit: approximately one page.
Situation | Extend existing refinery and import coverage into one integrated supply exhibit
Coverage | Evidence required | Exhibit treatment
Conventional refineries | Operating status, production, capacity and major changes over time. | Retain the refinery timeline; distinguish nameplate capacity from actual product output.
Secunda | Production trajectory, operating challenges and petrol/diesel yields. | Add time-series annotations or a callout showing the implications for liquid-fuel supply.
Mossgas / PetroSA | Plant-specific shutdown dates, operating status and lost fuel production. | Distinguish stopped production from permanent closure; verify the status before labelling.
Imports | Existing import series reconciled with domestic production and demand. | Show changing import dependence; do not attribute every import increase to lost local supply.
Strictly Confidential
Notes: Source: user feedback and explicit scope sign-off in this conversation, 7 October 2026. Style and existing coverage references: Vopak_Convergence_current.pptx, inspected 7 October 2026. Repository boundaries: CLAUDE.md; GATE_CHECKLIST.md; workstreams/README.md. No new market research or quantitative findings are asserted. Existing pack starting points: slides 4, 6 and 26. Proposed integrated exhibit: approximately one page.

## Slide 6: Transport shifts could weaken historical support for petrol and diesel demand
1 Overview
2 Market baseline
3 Market changes
4 Vopak outlook
L / M / H describes the level of each input; it does not automatically indicate the direction of total fuel demand.
Complication 1 | Economic recovery may be partly offset by structural changes
Change to test | Scenario levers | Demand translation
Road freight returns to rail | High / medium / low rail recovery by corridor; capacity delivery, utilisation and transferable freight. | Estimate displaced road tonne-kilometres and fuel, allowing for additional diesel rail traction.
EV adoption accelerates | EV purchase-price declines, fuel/electricity costs and fleet replacement. | Link ownership economics to adoption; distinguish temporary price shocks from sustained incentives.
Vehicles become more efficient | Efficiency gains by segment, real-world adjustment, mileage and fleet turnover. | Apply gains to incoming cohorts; avoid double counting vehicles already shifted to EVs.
Growth improves or stalls | GDP, sector activity and investment outcomes. | Treat growth as a common scenario assumption. Avoid adding FDI/confidence multipliers on top of the same GDP effect.
Strictly Confidential
Notes: Source: user feedback and explicit scope sign-off in this conversation, 7 October 2026. Style and existing coverage references: Vopak_Convergence_current.pptx, inspected 7 October 2026. Repository boundaries: CLAUDE.md; GATE_CHECKLIST.md; workstreams/README.md. No new market research or quantitative findings are asserted. L / M / H describes the level of each input; it does not automatically indicate the direction of total fuel demand.

## Slide 7: Power-system recovery could persist or reverse
1 Overview
2 Market baseline
3 Market changes
4 Vopak outlook
Link to the Eskom volumes, expenditure and EAF exhibit. No scenario values or completed demand estimates are approved here.
Complication 2 | Keep power and load shedding as a standalone scenario question
Scenario driver | Levers to test | Implication to quantify
Sustained recovery | Higher or sustained EAF and fewer fleet breakdowns. | Whether lower diesel generation can persist, and how much historical demand support unwinds.
Availability setbacks | Lower EAF, outages and major fleet breakdowns. | Additional residual generation needs and feasible diesel dispatch.
Retirement before replacement | Earlier decommissioning; delayed wind, solar or gas capacity and commissioning. | The timing and scale of any supply gap; installed capacity alone is not dependable generation.
Eskom and private response | Diesel generation availability, fuel consumption and operating constraints; non-Eskom response. | Estimate Eskom diesel and backup/self-generation separately. Do not equate Eskom diesel dispatch directly with load shedding.
Strictly Confidential
Notes: Source: user feedback and explicit scope sign-off in this conversation, 7 October 2026. Style and existing coverage references: Vopak_Convergence_current.pptx, inspected 7 October 2026. Repository boundaries: CLAUDE.md; GATE_CHECKLIST.md; workstreams/README.md. No new market research or quantitative findings are asserted. Link to the Eskom volumes, expenditure and EAF exhibit. No scenario values or completed demand estimates are approved here.

## Slide 8: Domestic fuel supply could recover or contract further
1 Overview
2 Market baseline
3 Market changes
4 Vopak outlook
Existing pack starting points: slides 6, 18 and 27. Restart and gas assumptions require explicit confirmation.
Complication 3 | Production changes alter import requirements for a given demand level
Supply uncertainty | Levers to develop | Evidence or definition needed
Major refinery restart | Restart timing, commissioning ramp-up, utilisation and petrol/diesel yields. | Confirm the facility and proposal; distinguish ambition, financed commitment and achievable output.
Secunda production | Gas-related production improvement, availability and product allocation. | Clarify the intended gas driver and substantiate its effect on output. Test any diversion away from liquid fuels.
Natref's future | Continued operation, investment, utilisation or reduced output. | Establish the operating outlook, required investment and credible alternatives.
Import consequences | Combined domestic production paths against each demand scenario. | Quantify imports consistently. Diversion away from fuel production constrains domestic supply, not end-user demand.
Strictly Confidential
Notes: Source: user feedback and explicit scope sign-off in this conversation, 7 October 2026. Style and existing coverage references: Vopak_Convergence_current.pptx, inspected 7 October 2026. Repository boundaries: CLAUDE.md; GATE_CHECKLIST.md; workstreams/README.md. No new market research or quantitative findings are asserted. Existing pack starting points: slides 6, 18 and 27. Restart and gas assumptions require explicit confirmation.

## Slide 9: Competing corridors could change how inland fuel demand is served
1 Overview
2 Market baseline
3 Market changes
4 Vopak outlook
Existing pack starting points: slides 7-8, 11 and 23. Fuel distribution competition is distinct from the road-to-rail demand lever.
Complication 4 | Compare access and delivered economics within each reachable market
Corridor | Comparison needed | Levers and output
Durban | Road and rail costs, capacity, reliability and constraints; pipeline benchmark. | Test route competitiveness, bottlenecks and expansion; establish the accessible inland market.
Matola / Maputo | Reachable destinations, inland logistics, border constraints, costs and capacity. | Test whether feasible routes can capture demand currently or potentially served via Durban.
Walvis Bay | Reachable markets, distances, delivered costs, transit times and capacity. | Assess where it competes credibly; do not presume all inland markets are addressable.
Combined assessment | Corridor map and comparable delivered-cost/throughput assessment. | Allocate scenario flows with physical and commercial constraints. Higher SA imports do not automatically benefit Durban or Vopak.
Strictly Confidential
Notes: Source: user feedback and explicit scope sign-off in this conversation, 7 October 2026. Style and existing coverage references: Vopak_Convergence_current.pptx, inspected 7 October 2026. Repository boundaries: CLAUDE.md; GATE_CHECKLIST.md; workstreams/README.md. No new market research or quantitative findings are asserted. Existing pack starting points: slides 7-8, 11 and 23. Fuel distribution competition is distinct from the road-to-rail demand lever.

## Slide 10: The resolution must quantify Vopak's share and investment headroom
1 Overview
2 Market baseline
3 Market changes
4 Vopak outlook
Existing pack starting points: slides 9-11, 22-24 and 28. Market headroom is not itself a commercially justified investment.
Resolution | Report Durban and the Lesedi catchment separately
Required answer | Work needed | Decision exhibit
Current market share | Define catchments, products, period and addressable-market denominator; obtain comparable Vopak throughput. | Vopak throughput / relevant market throughput. Show storage-capacity share separately if used.
Future market share | Translate demand, supply and route scenarios into accessible volumes; account for competitors and customers. | Market size and Vopak throughput/share by scenario; avoid double counting transfers between locations.
Capacity headroom | Compare potential throughput with usable capacity, utilisation, bottlenecks and competitor expansion. | Existing capacity versus scenario requirements; distinguish gross tankage from effective capacity.
Investment case | Assess customer commitments, commercial terms, capex and required returns. | Whether, where, when and at what scale to invest; triggers for investment, phasing or deferral.
Strictly Confidential
Notes: Source: user feedback and explicit scope sign-off in this conversation, 7 October 2026. Style and existing coverage references: Vopak_Convergence_current.pptx, inspected 7 October 2026. Repository boundaries: CLAUDE.md; GATE_CHECKLIST.md; workstreams/README.md. No new market research or quantitative findings are asserted. Existing pack starting points: slides 9-11, 22-24 and 28. Market headroom is not itself a commercially justified investment.

## Slide 11: The agreed work sequence builds evidence before scenario conclusions
1 Overview
2 Market baseline
3 Market changes
4 Vopak outlook
No staffing dates or new deadlines are committed by this review. Automated checks do not replace peer review or business approval.
Delivery | Preserve the practical sequence agreed in the review
Step | Work | Completion evidence
1. Audit | Review the existing pack, data and model against the signed-off scope. | Covered / exhibit needed / verification needed / missing data / model development.
2. Define | Resolve corridors, catchment, share denominators, restart candidate and Secunda gas driver. | Explicit definitions and recorded decisions.
3. Evidence | Close source gaps and build situation exhibits. | Sources, periods, units and limitations documented.
4. Levers | Map evidence to existing or required model functionality. | Vintaged, registered assumptions; consistent boundaries and no double counting.
5. Scenarios | Run demand, supply, imports and routing to addressable Vopak throughput. | Coherent scenario outputs with traceable assumptions.
6. Resolution | Build market-share and investment exhibits; complete relevant checks and reviews. | Conditional conclusions, open limitations and review status.
Strictly Confidential
Notes: Source: user feedback and explicit scope sign-off in this conversation, 7 October 2026. Style and existing coverage references: Vopak_Convergence_current.pptx, inspected 7 October 2026. Repository boundaries: CLAUDE.md; GATE_CHECKLIST.md; workstreams/README.md. No new market research or quantitative findings are asserted. No staffing dates or new deadlines are committed by this review. Automated checks do not replace peer review or business approval.

## Slide 12: The audit must make every gap, decision and limitation traceable
1 Overview
2 Market baseline
3 Market changes
4 Vopak outlook
Source: signed-off conversation, 7 October 2026; repository architecture and release-gate documents. This is the approved work programme.
Execution control | Assign owners explicitly; do not infer evidence approval from scope sign-off
Control | Required record | Resolution trigger
Evidence tracker | Story point; exhibit; source; gap; lever; owner; resolution trigger; status. | Resolve each material gap before the related assumption or exhibit is adopted.
Definitions | Four road corridors; Lesedi catchment; market-share denominator; restart facility; Secunda gas driver. | Confirm before routing, share calculations or supply-case calibration.
Model boundary | Audit current scenario wiring and the additional routing, terminal-throughput and investment work needed. | National balances alone cannot establish Vopak share. Resolve functionality before presenting quantified resolution.
Review status | Record this conversation's scope approval separately from data verification, peer review and business approval. | Evidence acceptance before adoption; technical review before reliance; commercial approval before investment.
Responsibilities | Use existing workstream responsibilities as a starting point; assign individual items during the audit. | Named owners and expiry/resolution triggers for every unresolved input or technical limitation.
Strictly Confidential
Notes: Source: user feedback and explicit scope sign-off in this conversation, 7 October 2026. Style and existing coverage references: Vopak_Convergence_current.pptx, inspected 7 October 2026. Repository boundaries: CLAUDE.md; GATE_CHECKLIST.md; workstreams/README.md. No new market research or quantitative findings are asserted. Source: signed-off conversation, 7 October 2026; repository architecture and release-gate documents. This is the approved work programme.